## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
TEAM NAME | FiniteLoop
PROJECT NAME | Movieo - A Social Community for Lovers
PROJECT MENTOR | Mr. Srinivas (ANIPR Tech)
TEAM MEMBERS | Umesh Singla
Jaipal Singh
Varshit Battu
Punyaslok Pattnaik
Ram Kumar
Follow Readme on bitbucket also for more details.

## Team_Status
TEAM NAME | FiniteLoop
PROJECT NAME | Movieo - A Social Community for Lovers
PROJECT MENTOR | Mr. Srinivas (ANIPR Tech)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 5 (aug 30 - sept 6)
Learn using APIs | Requirements | All | 9 | 12 | Done | All told by client, everyone should be able to use APIs and that is the minimal requirement for the project.
Fetch data from Facebook/ Twitter | Preparation | All | 15 | -- | Delayed | Delayed due to lack of sufficient knowledge
Insert tweets into MySQL table taken from twitter | Requirements | Varshit,Ram | 7 | 8 | Done
Learn basics of android | Preparation | Jaipal | 12 | 17 | Done
Edit the movieo ppt | Design | Umesh, Client | -- | -- | Delayed | No clarification by the client, what to do and what not.
Week 6 (sept 7 - sept 13)
Install Android Studio | Preparation | Jaipal | 1.5 | 2 | Done |  | -0.5 | 25
Install gradles / plugins | Preparation | Jaipal | 1 | 2 | Ongoing |  | -1 | 50
Install PyCharm | Preparation | Varshit, Ram | 1 | 0.75 | Done |  | 0.25 | 33.3333
Install PyCharm / Any relevant IDE | Preparation | Punya | 1 | 1.2 | Ongoing | This is critical to project success | -0.2 | 16.6667
Django rest framework setup | Requirements | Varshit, Punya | 2.5 | 4 | Ongoing | Make sure scoping questions are included | -1.5 | 37.5
Configuring MongoDb | Requirements | Ram,Varshit | 1.5 | 1 | Ongoing |  | 0.5 | 50
Learning jQuery | Requirements | Umesh | 0 | 0 | Ongoing | Learning can never end, isn't it? | 0
Identify role owners | Preparation | All | 0.25 | 0.25 | Done | Finally, roles has been decided | 0 | 0
Team Meeting | Coordination | Umesh | 1 | 2 | Planned |  | -1 | 50
Status tracker | Documentation | Umesh | 1 | 1.5 | Done |  | -0.5 | 33.3333
*Ongoing - mostly because of mid sems
Week 7 (sept 14 - sept 20)
Learn about factories and services in AngularJS | Requirements | Umesh | 3 | 4 | Ongoing | using factories will make angular code efficient | -1 | 25
MongoDB | Requirements | Ram | 2 | 2 | Done
Facebook Login Integration back-end | Development | Ram, Varshit, Punya | 5 | 6.5 | Ongoing
Fetching data from FB/Twitter APIs | Development | Jaipal, Varshit | 4 | 4.5 | Done
List all use cases for SRS | Documentation | Jaipal, Punya | 1.5 | 1.5 | Done | For making SRS
Software Requirements Specification Document | Documentation | Umesh, Varshit, Ram | 4.5 | 6 | Done | Doc is still to be approved by client.
Team Meeting | Coordination | Umesh | 1 | 1 | Done
Status Tracker for this week. | Documentation | All | 2.75 | 3 | Done
Week 9 (sept 21 - sept 30)
Facebook Login Integration on Website | Development | Umesh | 2 | 2 | Done
Facebook Login Integration on App | Development | Jaipal | 4 | 4.5 | Done
Studying Django Rest framework | Preparation | Ram, Varshit, Punya | 5 | 6 | Ongoing
Making sample APIls in django and showing it to team | Development | Umesh | 5 | 5 | Done
Connecting django with MySQL instead of sqlite3 | Development | Ram, Varshit | 2 | 3 | Done
Designing the tables | Design | Punya, Varshit, Ram | 3 | 2 | Delayed | Rough Relational Schema uploaded but still not complete
Website: Front End Template Finalising | Design | Umesh, Jaipal | 1 | 1 | Done
Status Tracker for this period | Documentation | Umesh | 1 | 1 | Done
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15
Week 16
Week 17
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically

## Individual_Status
TEAM NAME | FiniteLoop
PROJECT NAME | Movieo - A Social Community for Lovers
PROJECT MENTOR | Mr. Srinivas (ANIPR Tech)
Actvities | Jaipal Singh Goud |  | Umesh Singla |  | Varshit Battu |  | Punyaslok Pattnaik |  | Ram Kumar |  | Estimated Total Hours | Actual Total Hours
| Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent
Week 5 & Week 6 (aug 30 - sept 14)
Install Android Studio | 1.5 | 2 | [8 empty] | 1.5 | 2
Install gradles / plugins | 1 | 2 | [8 empty] | 1 | 2
Install PyCharm |  |  |  |  | 0.5 | 0.25 | 0.25 | 0.5 | 0.5 | 0.25 | 1.25 | 1
Install PyCharm / Any relevant IDE |  |  |  |  | 0.5 | 0.25 | 0.25 | 0.5 | 0.5 | 0.25 | 1.25 | 1
Django rest framework setup |  |  | 1 | 2 | 1 | 0.5 | 1 | 1.5 | 1 | 1 | 4 | 5
Configuring MongoDb |  |  |  |  | 1 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 2 | 2
Learning jQuery |  |  | 4 | 5 | [6 empty] | 4 | 5
Learning threeJS |  |  | 1 | 1.5 | [6 empty] | 1 | 1.5
Identify role owners | 0.25 | 0.5 | 0.3 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.75 | 1 | 2.8 | 3.5
Team Meeting | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 3.75 | 3.75
Status tracker | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 2 | 2.5
Week 7 (sept 14 - sept 20)
Learn about factories and services in AngularJS |  |  | 3 | 4 | [6 empty] | 3 | 4
MongoDB | [8 empty] | 2 | 2 | 2 | 2
Facebook Login Integration |  |  |  |  | 2 | 2.5 | 1.5 | 2 | 1.5 | 2 | 5 | 6.5
Fetching data from FB/Twitter APIs | 4 | 4.5 |  |  | 4 | 4.5 |  |  |  |  | 8 | 9
List all use cases for SRS | 1.5 | 1.5 |  |  |  |  | 1.5 | 1.5 |  |  | 3 | 3
Software Requirements Specification Document |  |  | 1.5 | 2 | 1.5 | 2 |  |  | 1.5 | 2 | 4.5 | 6
Team Meeting |  |  | 1 | 1 | [6 empty] | 1 | 1
Status Tracker for this week. | 0.5 | 0.5 | 0.75 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.75 | 3
[11 empty] | 0 | 0
Week 9 (sept 21 - sept 30) | [10 empty] | 0 | 0
[11 empty] | 0 | 0
Facebook Login Integration on Website |  |  | 2 | 2 | [6 empty] | 2 | 2
Facebook Login Integration on App | 4 | 4.5 | [8 empty] | 4 | 4.5
Studying Django Rest framework |  |  |  |  | 5 | 5 | 5 | 6 | 5 | 6 | 15 | 17
Making sample APIls in django and showing it to team |  |  | 5 | 5 | [6 empty] | 5 | 5
Connecting django with MySQL instead of sqlite3 |  |  |  |  | 1 | 1.5 |  |  | 1 | 1.5 | 2 | 3
Designing the tables |  |  |  |  | 3 | 2 | 3 | 2 | 3 | 2 | 9 | 6
Website: Front End Template Finalising | 0.5 | 0.5 | 0.5 | 0.5 | [6 empty] | 1 | 1
Status Tracker for this week |  |  | 1 | 1 | [6 empty] | 1 | 1
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 14 | [10 empty] | 0 | 0
Migrate to Cross Platform | 6 | 9 | [8 empty] | 6 | 9
Designed and Created Database |  |  |  |  | 3 | 3 | 5 | 6 | 3 | 3 | 11 | 12
Created Barebone Structure for Web App UI |  |  | 7 | 8 | [6 empty] | 7 | 8
0 | [10 empty] | 0 | 0
Week 15 | [10 empty] | 0 | 0
Design Login Interface and Created Mock Design of app workflow | 12 | 19 | [8 empty] | 12 | 19
Created various GET APIs for Web App |  |  |  |  | 3 | 3.5 | 5 | 6 | 4.5 | 5 | 12.5 | 14.5
Created Dedicated Movie and Actor Pages |  |  | 5 | 7 | [6 empty] | 5 | 7
Week 16 | [10 empty] | 0 | 0
Integrate Tweets According to Hashtags | 7 | 7.5 | [8 empty] | 7 | 7.5
Created GET APIs for Actor and Movie Pages |  |  |  |  | 2 | 3 | 3.5 | 5 | 4 | 4 | 9.5 | 12
Created Admin Page for Custom Inputs |  |  |  |  | 3 | 3.5 | 1 | 1.5 | 2 | 2 | 6 | 7
Integrated Twitteer Feeds and Facebook Posts for each Movie based on Admin hashtag inputs |  |  | 4 | 6.5 | [6 empty] | 4 | 6.5
Week 17 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0