## Instructions
Using the Status tracker
TEAM NAME | FiniteLoop
PROJECT NAME | Movieo - A Social Community for Lovers
PROJECT MENTOR | Mr. Srinivas Reddy (ANIPR Tech)
TEAM MEMBERS | Umesh Singla
Jaipal Singh
Varshit Battu
Punyaslok Pattnaik
Ram Kumar
Follow Readme on bitbucket for more details.

## Team_Status
TEAM NAME | FiniteLoop
PROJECT NAME | Movieo - A Social Community for Lovers
PROJECT MENTOR | Mr. Srinivas Reddy (ANIPR Tech)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 5 (Work Period: aug 30 - sept 6)
Learn using APIs | Requirements | All | 9 | 12 | Done | All told by client, everyone should be able to use APIs and that is the minimal requirement for the project.
Fetch data from Facebook/ Twitter | Preparation | All | 15 | -- | Delayed | Delayed due to lack of sufficient knowledge
Insert tweets into MySQL table taken from twitter | Requirements | Varshit,Ram | 7 | 8 | Done
Learn basics of android | Preparation | Jaipal | 12 | 17 | Done
Edit the movieo ppt | Design | Umesh, Client | -- | -- | Delayed | No clarification by the client, what to do and what not.
Week 6 (Work Period: sept 7 - sept 13)
Install Android Studio | Preparation | Jaipal | 1.5 | 2 | Done |  | -0.5 | 25
Install gradles / plugins | Preparation | Jaipal | 1 | 2 | Ongoing |  | -1 | 50
Install PyCharm | Preparation | Varshit, Ram | 1 | 0.75 | Done |  | 0.25 | 33.33333333
Install PyCharm / Any relevant IDE | Preparation | Punya | 1 | 1.2 | Ongoing | This is critical to project success | -0.2 | 16.66666667
Django rest framework setup | Requirements | Varshit, Punya | 2.5 | 4 | Ongoing | Make sure scoping questions are included | -1.5 | 37.5
Configuring MongoDb | Requirements | Ram,Varshit | 1.5 | 1 | Ongoing |  | 0.5 | 50
Learning jQuery | Requirements | Umesh | 0 | 0 | Ongoing | Learning can never end, isn't it? | 0
Identify role owners | Preparation | All | 0.25 | 0.25 | Done | Finally, roles has been decided | 0 | 0
Team Meeting | Coordination | Umesh | 1 | 2 | Planned |  | -1 | 50
Status tracker | Documentation | Umesh | 1 | 1.5 | Done |  | -0.5 | 33.33333333
*Ongoing - mostly because of mid sems
Week 7 (Work Period: sept 14 - sept 20)
Learn about factories and services in AngularJS | Requirements | Umesh | 3 | 4 | Ongoing | using factories will make angular code efficient | -1 | 25
MongoDB | Requirements | Ram | 2 | 2 | Done
Facebook Login Integration back-end | Development | Ram, Varshit, Punya | 5 | 6.5 | Ongoing
Fetching data from FB/Twitter APIs | Development | Jaipal, Varshit | 4 | 4.5 | Done
List all use cases for SRS | Documentation | Jaipal, Punya | 1.5 | 1.5 | Done | For making SRS
Software Requirements Specification Document | Documentation | Umesh, Varshit, Ram | 4.5 | 6 | Done | Doc is still to be approved by client.
Team Meeting | Coordination | Umesh | 1 | 1 | Done
Status Tracker for this week. | Documentation | All | 2.75 | 3 | Done
Week 9, 10 (Work Period: sept 21 - sept 30)
Facebook Login Integration on Website | Development | Umesh | 2 | 2 | Done
Facebook Login Integration on App | Development | Jaipal | 4 | 4.5 | Done
Studying Django Rest framework | Preparation | Ram, Varshit, Punya | 5 | 6 | Ongoing
Making sample APIls in django and showing it to team | Development | Umesh | 5 | 5 | Done
Connecting django with MySQL instead of sqlite3 | Development | Ram, Varshit | 2 | 3 | Done
Designing the tables | Design | Punya, Varshit, Ram | 3 | 2 | Delayed | Rough Relational Schema uploaded but still not complete
Website: Front End Template Finalising | Design | Umesh, Jaipal | 1 | 1 | Done
Status Tracker for this period | Documentation | Umesh | 1 | 1 | Done
Week 11, 12 (Work Period: oct 4 - oct 18)
App migrated to Cross Platform | Development | Jaipal | 9 | 12 | Done |  | -3 | 25
R1 Presentation | Documentation | All | 5 | 5.5 | Done |  | -0.5 | 9.090909091
Created Barebone Structure for Web App | Development | Umesh | 5 | 6 | Done |  | -1 | 16.66666667
Database coded in django | Development | Punya, Varshit, Ram, Umesh | 12 | 14 | Done
Design Login Interface and Created Mock Design of app workflow | Design | Jaipal | 12 | 18 | Ongoing
Created various GET APIs for Web App | Development | Punya, Varshit, Ram, Umesh | 14.5 | 16.5 | Ongoing
Using GET APIs from Angular | Development | Umesh | 2 | 2 | Done
Created Dedicated Movie and Actor Pages | Development | Umesh | 5 | 6 | Done
Week 13 (oct 19 - oct 25, Work Period: oct 24 - oct 25)
Learn how to effectively use Facebook and Twitter APIs in the application | Preparation | Umesh, Varshit | 4.25 | 5 | Ongoing |  | -0.75 | 15
Connect mobile app with back-end | Development | Jaipal | 5 | 6 | Ongoing
*Ongoing - mostly because of monsoon break
Week 14 (Work Period: oct 26 - nov 3)
Constructing widgets on Twitter and use on website | Development | Umesh | 2 | 2 | Done |  | 0 | 0
Facebook widgets and screen examples on website | Development | Umesh | 2 | 2 | Done |  | 0 | 0
Integrate Tweets According to Hashtags | Development | Jaipal | 7 | 7.5 | Ongoing
Created Admin Pages for uploading data | Development | Punya, Varshit, Ram | 6.5 | 7.5 | Done
Creating dummy database for testing purposes | Development | Umesh, Punya, Varshit | 2.5 | 2.25 | Done
Created Admin Pages for custom inputs | Development | Punya, Varshit, Ram | 6 | 7 | Ongoing
Status Tracker for this week | Documentation | All | 2.5 | 2.75 | Done
Week 15 (Work Period: nov 4 - nov 12)
Deploying django code on pythonanywhere.com | Interfaces | Umesh | 3 | 3.5 | Done |  | -0.5 | 14.28571429
Admin interface bootstrapped | Development | Umesh | 0.5 | 0.5 | Done |  | 0 | 0
Sentimental Analysis APIs | Development | Varshit, Punya, Ram | 7 | 7 | Ongoing |  | 0 | 0
Finding source APIs for getting various values for tweets/user reviews passed | Requirements | Umesh, Punya, Ram | 4 | 4.5 | Ongoing |  | -0.5 | 11.11111111
Tweets Database | Development | Umesh, Punya | 1.5 | 2 | Delayed |  | -0.5 | 25
Custom Forms For handling Tweets | Development | Varshit, Ram | 5 | 6.5 | Ongoing |  | -1.5 | 23.07692308
API for reviews | Development | Umesh, Punya | 4 | 4.5 | Delayed |  | -0.5 | 11.11111111
Design Document | Documentation | Jaipal, Varshit, Ram, Punya, Umesh | 9 | 9.5 | Done |  | -0.5 | 5.263157895
Week 16 (Work Period: nov 13 - nov 23) - Includes Release II
Custom Forms For handling Tweets - admin tweet panel | Development | Umesh, Varshit | 5.5 | 6.5 | Done |  | -1 | 15.38461538
Tweets API for displaying on website | Development | Punya, Umesh | 6 | 7 | Done
Integrating Twitter API in backend | Testing | Punya, Varshit | 9 | 12 | Planned |  | -3 | 25
Integrating Alchemi API for highcharts, sentiment analysis, keyword extraction | Testing | Punya, Umesh | 9 | 12 | Done |  | -3 | 25
Actor Page design for Mobile | Development | Jaipal | 2 | 2.5 | Done |  | -0.5 | 20
Movies Page for app, reviews display, pie chart for analysis, navigation menu, integrating with backend | Development | Jaipal | 20 | 25 | Done | individual movie pages | -5 | 20
Movie Page for website, including displaying tweets, twitter widget, loaders for positivity %, review form to display, search bar, rating to be displayed using stars, integrating fb login with backend & saving user details for first time login, dashboard page | Development | Umesh | 30 | 40 | Done
Check new user & add new user APIs | Testing | Punya, Umesh | 5.5 | 6.5 | Done |  | -1 | 15.38461538
popularity graph for a movie | Development | Punya | 2 | 2 | Done |  | 0 | 0
Finding sentimental analysis APIs and testing them | Testing | Punya, Varshit, Umesh, Ram | 8.5 | 11 | Ongoing |  | -2.5 | 22.72727273
Final deploying on pythonanywhere | Interfaces | Umesh | 2 | 4 | Done | deploying on some server | -2 | 50
populating data in database | Testing | Punya | 2 | 2.5 | Done |  | -0.5 | 20
finding photos for slider | Development | Punya | 1.5 | 1.5 | Done | photos to show on landing page | 0 | 0
Status Tracker For this week | Documentation | Umesh | 1 | 1.5 | Done | Finally it is the last status tracketr | -0.5 | 33.33333333
Release 2 presentation | Documentation | Umesh, Varshit | 1 | 1 | Done | Finally! | 0 | 0
Finding useful articles related to project and additional plugins | Documentation | Varshit, Ram | 6 | 6 | Ongoing | Motivation! | 0 | 0

## Individual_Status
TEAM NAME | FiniteLoop
PROJECT NAME | Movieo - A Social Community for Lovers
PROJECT MENTOR | Mr. Srinivas Reddy (ANIPR Tech)
Actvities | Jaipal Singh Goud |  | Umesh Singla |  | Varshit Battu |  | Punyaslok Pattnaik |  | Ram Kumar |  | Estimated Total Hours | Actual Total Hours
| Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent
Week 5 & Week 6 (Work Period: aug 30 - sept 14)
Install Android Studio | 1.5 | 2 | [8 empty] | 1.5 | 2
Install gradles / plugins | 1 | 2 | [8 empty] | 1 | 2
Install PyCharm |  |  |  |  | 0.5 | 0.25 | 0.25 | 0.5 | 0.5 | 0.25 | 1.25 | 1
Install PyCharm / Any relevant IDE |  |  |  |  | 0.5 | 0.25 | 0.25 | 0.5 | 0.5 | 0.25 | 1.25 | 1
Django rest framework setup |  |  | 1 | 2 | 1 | 0.5 | 1 | 1.5 | 1 | 1 | 4 | 5
Configuring MongoDb |  |  |  |  | 1 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 2 | 2
Learning jQuery |  |  | 4 | 5 | [6 empty] | 4 | 5
Learning threeJS |  |  | 1 | 1.5 | [6 empty] | 1 | 1.5
Identify role owners | 0.25 | 0.5 | 0.3 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.75 | 1 | 2.8 | 3.5
Team Meeting | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 3.75 | 3.75
Status tracker | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 2 | 2.5
Week 7 (Work Period: sept 14 - sept 20)
Learn about factories and services in AngularJS |  |  | 3 | 4 | [6 empty] | 3 | 4
MongoDB | [8 empty] | 2 | 2 | 2 | 2
Facebook Login Integration |  |  |  |  | 2 | 2.5 | 1.5 | 2 | 1.5 | 2 | 5 | 6.5
Fetching data from FB/Twitter APIs | 4 | 4.5 |  |  | 4 | 4.5 |  |  |  |  | 8 | 9
List all use cases for SRS | 1.5 | 1.5 |  |  |  |  | 1.5 | 1.5 |  |  | 3 | 3
Software Requirements Specification Document |  |  | 1.5 | 2 | 1.5 | 2 |  |  | 1.5 | 2 | 4.5 | 6
Team Meeting |  |  | 1 | 1 | [6 empty] | 1 | 1
Status Tracker for this week | 0.5 | 0.5 | 0.75 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.75 | 3
Created Barebone Structure for Web App | [10 empty] | 0 | 0
Week 9, 10 (Work Period: sept 21 - sept 30) | [10 empty] | 0 | 0
[11 empty] | 0 | 0
Facebook Login Integration on Website |  |  | 2 | 2 | [6 empty] | 2 | 2
Facebook Login Integration on App | 4 | 4.5 | [8 empty] | 4 | 4.5
Studying Django Rest framework |  |  |  |  | 5 | 5 | 5 | 6 | 5 | 6 | 15 | 17
Making sample APIls in django and showing it to team |  |  | 5 | 5 | [6 empty] | 5 | 5
Connecting django with MySQL instead of sqlite3 |  |  |  |  | 1 | 1.5 |  |  | 1 | 1.5 | 2 | 3
Designing the tables |  |  |  |  | 3 | 2 | 3 | 2 | 3 | 2 | 9 | 6
Website: Front End Template Finalising | 0.5 | 0.5 | 0.5 | 0.5 | [6 empty] | 1 | 1
Status Tracker for this week |  |  | 1 | 1 | [6 empty] | 1 | 1
Deploying django code on pythonanywhere.com | [10 empty] | 0 | 0
Week 11, 12 (Work Period: oct 4 - oct 18) - Includes Release l | [10 empty] | 0 | 0
App migrated to Cross Platform | 9 | 12 | [8 empty] | 9 | 12
R1 Presentation | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 5 | 5.5
Created Barebone Structure for Web App |  |  | 5 | 6 | [6 empty] | 5 | 6
Database coded in django |  |  | 2 | 2 | 2 | 3 | 5 | 6 | 3 | 3 | 12 | 14
Design Login Interface and Created Mock Design of app workflow | 12 | 18 | [8 empty] | 12 | 18
Created various GET APIs for Web App |  |  | 2 | 2 | 3 | 3.5 | 5 | 6 | 4.5 | 5 | 14.5 | 16.5
Using GET APIs from Angular |  |  | 2 | 2 | [6 empty] | 2 | 2
Created Dedicated Movie and Actor Pages |  |  | 5 | 6 | [6 empty] | 5 | 6
[11 empty] | 0 | 0
Week 13 (oct 19 - oct 25, Work Period: oct 24 - oct 25) | [10 empty] | 0 | 0
A little break from work
Learn how to effectively use Facebook and Twitter APIs in the application |  |  | 2.25 | 3 | 2 | 2 |  |  |  |  | 4.25 | 5
Connect mobile app with back-end | 5 | 6 | [8 empty] | 5 | 6
Week 14 (Work Period: oct 26 - nov 3) | [10 empty] | 0 | 0
Constructing widgets on Twitter and use on website |  |  | 2 | 2 | [6 empty] | 2 | 2
Facebook widgets and screen examples on website |  |  | 2 | 2 | [6 empty] | 2 | 2
Integrate Tweets According to Hashtags | 7 | 7.5 | [8 empty] | 7 | 7.5
Created Admin Pages for uploading data |  |  |  |  | 3 | 3 | 1 | 1.5 | 2.5 | 3 | 6.5 | 7.5
Creating dummy database for testing purposes |  |  | 0.5 | 0.5 | 1 | 1 | 1 | 0.75 |  |  | 2.5 | 2.25
Created Admin Pages for custom inputs |  |  |  |  | 3 | 3.5 | 1 | 1.5 | 2 | 2 | 6 | 7
Status Tracker for this week | 0.5 | 0.5 | 0.5 | 0.75 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5 | 2.75
Week 15 (Work Period: nov 4 - nov 12) | [10 empty] | 0 | 0
[11 empty] | 0 | 0
Deploying django code on pythonanywhere.com |  |  | 3 | 3.5 | [6 empty] | 3 | 3.5
Admin interface bootstrapped |  |  | 0.5 | 0.5 | [6 empty] | 0.5 | 0.5
Sentimental Analysis APIs |  |  |  |  | 4 | 4 | 1 | 1 | 2 | 2 | 7 | 7
Finding source APIs for getting various values for tweets/user reviews passed |  |  | 0.5 | 0.5 | 2 | 2.5 |  |  | 1.5 | 1.5 | 4 | 4.5
Tweets Database |  |  | 0.5 | 0.5 |  |  | 1 | 1.5 |  |  | 1.5 | 2
Custom Forms For handling Tweets |  |  |  |  | 3 | 4 |  |  | 2 | 2.5 | 5 | 6.5
API for reviews |  |  | 1 | 1 |  |  | 3 | 3.5 |  |  | 4 | 4.5
Design Document | 1.5 | 2 | 0.5 | 0.5 | 2 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 9 | 9.5
[11 empty] | 0 | 0
Week 16 (Work Period: nov 13 - nov 23) - Includes Release ll | [10 empty] | 0 | 0
Custom Forms For handling Tweets - admin tweet panel |  |  | 5 | 6 | 0.5 | 0.5 |  |  |  |  | 5.5 | 6.5
Tweets API for displaying on website |  |  | 1 | 1 |  |  | 5 | 6 |  |  | 6 | 7
Integrating Twitter API in backend |  |  |  |  | 3 | 4 | 4 | 5.5 | 2 | 2.5 | 9 | 12
Integrating Alchemi API for highcharts, sentiment analysis, keyword extraction |  |  | 4 | 5.5 |  |  | 5 | 6.5 |  |  | 9 | 12
Actor Page design for Mobile | 2 | 2.5 | [8 empty] | 2 | 2.5
Movies Page for app, reviews display, pie chart for analysis, navigation menu, integrating with backend | 20 | 25 | [8 empty] | 20 | 25
Movie Page for website, including displaying tweets, twitter widget, loaders for positivity %, review form to display, search bar, rating to be displayed using stars, integrating fb login with backend & saving user details for first time login, dashboard page |  |  | 30 | 40 | [6 empty] | 30 | 40
Check new user & add new user APIs |  |  | 2 | 2 |  |  | 3.5 | 4.5 |  |  | 5.5 | 6.5
popularity graph for a movie |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 2 | 2
Finding sentimental analysis APIs and testing them |  |  | 0.5 | 0.5 | 3 | 4 | 3 | 4 | 2 | 2.5 | 8.5 | 11
Final deploying on pythonanywhere |  |  | 2 | 4 | [6 empty] | 2 | 4
populating data in database |  |  | 0.5 | 0.5 |  |  | 1.5 | 2 |  |  | 2 | 2.5
finding photos for slider | [6 empty] | 1.5 | 1.5 |  |  | 1.5 | 1.5
Status Tracker For this week |  |  | 1 | 1.5 | [6 empty] | 1 | 1.5
Release 2 presentation |  |  | 1 | 1 | [6 empty] | 1 | 1
Finding useful articles related to project and additional plugins |  |  |  |  | 3 | 3 |  |  | 3 | 3 | 6 | 6
[11 empty] | 0 | 0
Time (in hours) | [10 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0